# ATEC Training Rollout, UAT & Sign-off Plan

ATEC-TRN-ROL-001  |  Version 0.96 PARTIAL LOCAL UAT - PRODUCTION UAT PENDING  |  Audit baseline: repository baseline 42c4dd6f plus approved readiness improvements, 8 August 2026

| Controlled field | Value |
| --- | --- |
| Document owner | ATEC Operations / System Owner |
| Process owners | Operations, Inspection, HR/Payroll |
| Classification | Internal controlled training document |
| Status | Local admin UI and role API checks passed; production role UI, delivery and screenshots pending |
| Review cycle | Annual and after material system/workflow change |

APPROVAL GATE: Do not issue as final employee instruction until role-based live UAT passes and the screenshot register is captured from the approved live or training environment.

# Rollout principle

Release training only after the same approved workflow is proven role by role. Treat the manual, videos, assessment and system build as one controlled set; a workflow change requires synchronized revision.

# Phases and hold points

| Phase | Owner | Activities | Hold point / evidence |
| --- | --- | --- | --- |
| 1. Workflow decision | System Owner + Ops | Review audit findings; choose source of truth for hours; agree return/correction and assistant access. | HP1 signed workflow decision. |
| 2. Fix/UAT preparation | Product + IT | Verify the implemented P0 controls; seed synthetic Job 11927; create role accounts. | HP2 test environment and data approved. |
| 3. Role-based UAT | Ops, Inspection, HR | Walk job card → inspection → My Day → approvals → payroll → Accelo. | HP3 UAT evidence; no unresolved critical defects. |
| 4. Capture and production | Training Lead | Capture screenshots; record videos; add captions; update manual labels. | HP4 content review by each process owner. |
| 5. Pilot | Selected lead, assistant, manager, HR | Facilitated training, written and practical assessment, feedback. | HP5 pilot competence and issue closure. |
| 6. Deployment | Managers | Role-based sessions; supervised first live job/day; sign-offs. | HP6 access released only to competent users. |
| 7. Sustainment | Document Controller | Version control, refresher training, change triggers, monthly sample review. | Quarterly effectiveness review. |

# Live UAT script

- Admin/Manager creates synthetic Job 11927 and assigns lead + assistant. Verify assignment visibility and email success/failure behavior.

- Lead records the exact sample timeline, adds evidence and submits. Simulate a timeline-copy failure once; verify recovery is controlled and idempotent.

- Inspector creates a linked inspection with the same numeric job number. Verify intended job-card identity and certificate linkage.

- Lead and assistant each open My Day. Deliberately create one wrong copied time; test audited employee Edit/Delete and the controlled return path.

- Manager verifies the employee audit change, performs one manager correction with reason, returns one sheet, then approves corrected sheets. Verify audit history and PDFs.

- HR accepts; run history filters and payroll export. Reconcile employee/day/job totals.

- Manager approves job card, runs Accelo readiness, verifies expected certificate, sends to test Accelo address and confirms receipt.

- Repeat an overnight/multi-day job and a critical-deviation/NOT SAFE scenario.

# Training delivery matrix

| Audience | Required modules | Practical demonstration | Authorization |
| --- | --- | --- | --- |
| Assistant/Employee | 1, 5, 6, 10 | My Day review, exception, safe error handling, submit | Manager sign-off |
| Lead Inspector | 1–6, 9, 10 | Assigned job, timeline, evidence, inspection, submission | Inspection + Ops sign-off |
| Manager | 1–7, 9, 10 | Allocate, correct/return/approve, readiness | System Owner sign-off |
| HR | 1, 6, 8, 10 | Accept/return, reports, payroll reconciliation | HR Manager sign-off |
| Admin | All | Full workflow, configuration and incident controls | System Owner sign-off |

# Suggested schedule

| Day | Activity |
| --- | --- |
| T-10 to T-7 | Workflow decisions and fixes/interim controls |
| T-6 | Role-based UAT |
| T-5 to T-3 | Screenshot/video production and review |
| T-2 | Pilot and corrections |
| T-1 | Final document approval and version freeze |
| T0 | Training deployment |
| T+1 to T+5 | Supervised use and daily issue review |
| T+30 | Effectiveness review and refresher decisions |

# Success measures

100% of in-scope employees trained and signed off before independent use.

No duplicate time created as a correction method.

At least 95% first-pass timesheet acceptance after the pilot period.

Every sampled inspection job has correct job-card/certificate linkage.

Every payroll export reconciles to HR-accepted sheets.

Every training issue is logged with owner, priority, due date and closure evidence.

# Change-control triggers

Job-card field, state or validation change.

Timesheet calculation, correction, approval or export change.

Role/permission change.

Inspection wizard, safety rule or certificate linkage change.

Accelo delivery/readiness change.

A recurring user error or audit finding.

# Final rollout authorization

| Approval | Decision | Name/signature/date |
| --- | --- | --- |
| Operations workflow | Approve / Hold | ________________________ |
| Inspection safety content | Approve / Hold | ________________________ |
| HR/payroll content | Approve / Hold | ________________________ |
| IT/live verification | Approve / Hold | ________________________ |
| Document control release | Approve / Hold | ________________________ |

# Document approval

| Role | Name / position | Signature | Date |
| --- | --- | --- | --- |
| Prepared by | ________________ | ________________ | ________ |
| Workflow reviewed by | ________________ | ________________ | ________ |
| HR/Payroll reviewed by | ________________ | ________________ | ________ |
| Approved by | ________________ | ________________ | ________ |

## Revision history

| Version | Date | Change | Approval |
| --- | --- | --- | --- |
| 0.95 | 08 Aug 2026 | Approved readiness improvements implemented; pending live UAT and controlled release. | Pending |
| 0.96 | 08 Aug 2026 | HP2 local checkpoint recorded; HP3 deployed role walkthrough remains open. | Pending |

# Local UAT checkpoint - 8 August 2026

HP2 is partially satisfied: the local system started successfully, key admin screens rendered, and Manager/Inspector/Assistant/HR API authorization checks returned the expected access boundaries.

HP3 remains open. Required evidence is an interactive role-by-role walkthrough in the approved deployed environment using synthetic Job 11927, followed by approved screenshots and process-owner sign-off.